## Sprint-2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 3. Account Management | 3.2 | Account Settings | Create UI components for account settings | Y | 2025-03-27 | 2025-03-29 | 100% | Asritha Pallapotu
2 | 3. Account Management | 3.2 | Account Settings | Implement backend logic to update account preferences | Y | 2025-03-27 | 2025-03-27 | 100% | Yugantkumar Gajera
3 | 3. Account Management | 3.2 | Account Settings | Add field validations for email/password change | N | 2025-03-27 | 2025-03-27 | 100% | Sai Aneesh
4 | 3. Account Management | 3.2 | Account Settings | Set up data flow between UI and API for account settings | N | 2025-03-27 | 2025-03-29 | 100% | Dhvani Dilipbhai Borda
5 | 3. Account Management | 3.2 | Account Settings | Perform functional testing for account update scenarios | Y | 2025-03-27 | 2025-03-27 | 100% | Naveen Kumar Kukutla
6 | 3. Account Management | 3.2 | Account Settings | Create UI components for account settings | N | 2025-03-28 | 2025-03-28 | 100% | Yugantkumar Gajera
7 | 3. Account Management | 3.2 | Account Settings | Implement backend logic to update account preferences | N | 2025-03-28 | 2025-03-30 | 100% | Akhil Yadati
8 | 3. Account Management | 3.2 | Account Settings | Add field validations for email/password change | N | 2025-03-28 | 2025-03-30 | 100% | Sai Aneesh
9 | 3. Account Management | 3.2 | Account Settings | Set up data flow between UI and API for account settings | Y | 2025-03-28 | 2025-03-29 | 100% | Syed Adnan
10 | 3. Account Management | 3.2 | Account Settings | Perform functional testing for account update scenarios | Y | 2025-03-28 | 2025-03-29 | 100% | Amar Gopal Kapalavai
11 | 3. Account Management | 3.2 | Account Settings | Create UI components for account settings | Y | 2025-03-28 | 2025-03-29 | 100% | Venkata Puneeth Nannapaneni
12 | 3. Account Management | 3.2 | Account Settings | Implement backend logic to update account preferences | Y | 2025-03-29 | 2025-03-31 | 100% | Naveen Kumar Kukutla
13 | 3. Account Management | 3.2 | Account Settings | Add field validations for email/password change | Y | 2025-03-29 | 2025-03-30 | 100% | Yugantkumar Gajera
14 | 3. Account Management | 3.2 | Account Settings | Set up data flow between UI and API for account settings | Y | 2025-03-29 | 2025-03-31 | 100% | Akhil Yadati
15 | 3. Account Management | 3.2 | Account Settings | Perform functional testing for account update scenarios | Y | 2025-03-30 | 2025-03-31 | 100% | Venkata Puneeth Nannapaneni
16 | 3. Account Management | 3.2 | Account Settings | Create UI components for account settings | Y | 2025-03-30 | 2025-03-30 | 100% | Sai Aneesh
17 | 3. Account Management | 3.2 | Account Settings | Implement backend logic to update account preferences | N | 2025-03-30 | 2025-04-01 | 100% | Yugantkumar Gajera
18 | 3. Account Management | 3.2 | Account Settings | Add field validations for email/password change | N | 2025-03-30 | 2025-03-30 | 100% | Jensikumari Ishvarbhai Jasoliya
19 | 3. Account Management | 3.2 | Account Settings | Set up data flow between UI and API for account settings | Y | 2025-03-30 | 2025-03-30 | 100% | Sai Aneesh
20 | 3. Account Management | 3.2 | Account Settings | Perform functional testing for account update scenarios | N | 2025-03-31 | 2025-04-01 | 100% | Dhvani Dilipbhai Borda
21 | 3. Account Management | 3.2 | Account Settings | Create UI components for account settings | N | 2025-03-31 | 2025-04-02 | 100% | Dhvani Dilipbhai Borda
22 | 3. Account Management | 3.2 | Account Settings | Implement backend logic to update account preferences | Y | 2025-03-31 | 2025-04-01 | 100% | Dhvani Dilipbhai Borda
23 | 3. Account Management | 3.3 | Profile Update and Management | Design profile update form layout | Y | 2025-03-31 | 2025-04-02 | 100% | Asritha Pallapotu
24 | 3. Account Management | 3.3 | Profile Update and Management | Implement image upload and preview logic | Y | 2025-03-31 | 2025-03-31 | 100% | Asritha Pallapotu
25 | 3. Account Management | 3.3 | Profile Update and Management | Validate profile field inputs (bio, portfolio, etc.) | Y | 2025-03-31 | 2025-04-02 | 100% | Akhil Yadati
26 | 3. Account Management | 3.3 | Profile Update and Management | Connect profile update form to database | N | 2025-04-01 | 2025-04-03 | 100% | Sai Aneesh
27 | 3. Account Management | 3.3 | Profile Update and Management | Verify update persistence and error handling | Y | 2025-04-01 | 2025-04-01 | 100% | Asritha Pallapotu
28 | 3. Account Management | 3.3 | Profile Update and Management | Design profile update form layout | Y | 2025-04-01 | 2025-04-02 | 100% | Amar Gopal Kapalavai
29 | 3. Account Management | 3.3 | Profile Update and Management | Implement image upload and preview logic | N | 2025-04-01 | 2025-04-02 | 100% | Akhil Yadati
30 | 3. Account Management | 3.3 | Profile Update and Management | Validate profile field inputs (bio, portfolio, etc.) | Y | 2025-04-02 | 2025-04-03 | 100% | Syed Adnan
31 | 3. Account Management | 3.3 | Profile Update and Management | Connect profile update form to database | Y | 2025-04-02 | 2025-04-03 | 100% | Venkata Puneeth Nannapaneni
32 | 3. Account Management | 3.3 | Profile Update and Management | Verify update persistence and error handling | N | 2025-04-02 | 2025-04-03 | 100% | Venkata Puneeth Nannapaneni
33 | 3. Account Management | 3.3 | Profile Update and Management | Design profile update form layout | N | 2025-04-03 | 2025-04-03 | 100% | Naveen Kumar Kukutla
34 | 3. Account Management | 3.3 | Profile Update and Management | Implement image upload and preview logic | N | 2025-04-03 | 2025-04-04 | 100% | Amar Gopal Kapalavai
35 | 3. Account Management | 3.3 | Profile Update and Management | Validate profile field inputs (bio, portfolio, etc.) | Y | 2025-04-03 | 2025-04-03 | 100% | Naveen Kumar Kukutla
36 | 3. Account Management | 3.3 | Profile Update and Management | Connect profile update form to database | Y | 2025-04-03 | 2025-04-05 | 100% | Sai Aneesh
37 | 3. Account Management | 3.3 | Profile Update and Management | Verify update persistence and error handling | N | 2025-04-04 | 2025-04-05 | 100% | Akhil Yadati
38 | 3. Account Management | 3.3 | Profile Update and Management | Design profile update form layout | Y | 2025-04-04 | 2025-04-06 | 100% | Syed Adnan
39 | 3. Account Management | 3.3 | Profile Update and Management | Implement image upload and preview logic | N | 2025-04-04 | 2025-04-06 | 100% | Venkata Puneeth Nannapaneni
40 | 3. Account Management | 3.3 | Profile Update and Management | Validate profile field inputs (bio, portfolio, etc.) | N | 2025-04-04 | 2025-04-05 | 100% | Jensikumari Ishvarbhai Jasoliya
41 | 3. Account Management | 3.3 | Profile Update and Management | Connect profile update form to database | Y | 2025-04-04 | 2025-04-06 | 100% | Jensikumari Ishvarbhai Jasoliya
42 | 3. Account Management | 3.3 | Profile Update and Management | Verify update persistence and error handling | N | 2025-04-05 | 2025-04-06 | 100% | Naveen Kumar Kukutla
43 | 3. Account Management | 3.3 | Profile Update and Management | Design profile update form layout | N | 2025-04-05 | 2025-04-05 | 100% | Venkata Puneeth Nannapaneni
44 | 3. Account Management | 3.3 | Profile Update and Management | Implement image upload and preview logic | Y | 2025-04-05 | 2025-04-05 | 100% | Syed Adnan
45 | 4. Job posting and Searching | 4.1 | Create Job Posting | Design gig creation form with all input fields | Y | 2025-04-05 | 2025-04-05 | 100% | Akhil Yadati
46 | 4. Job posting and Searching | 4.1 | Create Job Posting | Implement category and pricing logic for new gigs | N | 2025-04-05 | 2025-04-06 | 100% | Dhvani Dilipbhai Borda
47 | 4. Job posting and Searching | 4.1 | Create Job Posting | Connect frontend form to gig creation API | N | 2025-04-05 | 2025-04-05 | 100% | Sai Aneesh
48 | 4. Job posting and Searching | 4.1 | Create Job Posting | Add client-side validation for required fields | N | 2025-04-06 | 2025-04-08 | 100% | Jensikumari Ishvarbhai Jasoliya
49 | 4. Job posting and Searching | 4.1 | Create Job Posting | Test gig creation end-to-end including success/failure states | N | 2025-04-06 | 2025-04-07 | 100% | Amar Gopal Kapalavai
50 | 4. Job posting and Searching | 4.1 | Create Job Posting | Design gig creation form with all input fields | Y | 2025-04-06 | 2025-04-08 | 100% | Dhvani Dilipbhai Borda
51 | 4. Job posting and Searching | 4.1 | Create Job Posting | Implement category and pricing logic for new gigs | N | 2025-04-06 | 2025-04-06 | 100% | Syed Adnan
52 | 4. Job posting and Searching | 4.1 | Create Job Posting | Connect frontend form to gig creation API | N | 2025-04-07 | 2025-04-07 | 100% | Amar Gopal Kapalavai
53 | 4. Job posting and Searching | 4.1 | Create Job Posting | Add client-side validation for required fields | Y | 2025-04-07 | 2025-04-08 | 100% | Amar Gopal Kapalavai
54 | 4. Job posting and Searching | 4.1 | Create Job Posting | Test gig creation end-to-end including success/failure states | Y | 2025-04-07 | 2025-04-07 | 100% | Akhil Yadati
55 | 4. Job posting and Searching | 4.1 | Create Job Posting | Design gig creation form with all input fields | Y | 2025-04-07 | 2025-04-09 | 100% | Syed Adnan
56 | 4. Job posting and Searching | 4.1 | Create Job Posting | Implement category and pricing logic for new gigs | N | 2025-04-07 | 2025-04-09 | 100% | Venkata Puneeth Nannapaneni
57 | 4. Job posting and Searching | 4.1 | Create Job Posting | Connect frontend form to gig creation API | Y | 2025-04-07 | 2025-04-07 | 100% | Akhil Yadati
58 | 4. Job posting and Searching | 4.1 | Create Job Posting | Add client-side validation for required fields | N | 2025-04-08 | 2025-04-09 | 100% | Jensikumari Ishvarbhai Jasoliya
59 | 4. Job posting and Searching | 4.1 | Create Job Posting | Test gig creation end-to-end including success/failure states | N | 2025-04-08 | 2025-04-09 | 100% | Akhil Yadati
60 | 4. Job posting and Searching | 4.1 | Create Job Posting | Design gig creation form with all input fields | Y | 2025-04-08 | 2025-04-08 | 100% | Venkata Puneeth Nannapaneni
61 | 4. Job posting and Searching | 4.1 | Create Job Posting | Implement category and pricing logic for new gigs | N | 2025-04-09 | 2025-04-10 | 100% | Yugantkumar Gajera
62 | 4. Job posting and Searching | 4.1 | Create Job Posting | Connect frontend form to gig creation API | N | 2025-04-09 | 2025-04-09 | 100% | Asritha Pallapotu
63 | 4. Job posting and Searching | 4.1 | Create Job Posting | Add client-side validation for required fields | Y | 2025-04-09 | 2025-04-11 | 100% | Naveen Kumar Kukutla
64 | 4. Job posting and Searching | 4.1 | Create Job Posting | Test gig creation end-to-end including success/failure states | Y | 2025-04-09 | 2025-04-10 | 100% | Naveen Kumar Kukutla
65 | 4. Job posting and Searching | 4.1 | Create Job Posting | Design gig creation form with all input fields | N | 2025-04-09 | 2025-04-09 | 100% | Naveen Kumar Kukutla
66 | 4. Job posting and Searching | 4.1 | Create Job Posting | Implement category and pricing logic for new gigs | N | 2025-04-09 | 2025-04-09 | 100% | Naveen Kumar Kukutla
67 | 4. Job posting and Searching | 4.2 | Manage Job Application | Display active/completed orders dynamically | N | 2025-04-10 | 2025-04-10 | 100% | Asritha Pallapotu
68 | 4. Job posting and Searching | 4.2 | Manage Job Application | Implement logic to mark order statuses | Y | 2025-04-10 | 2025-04-10 | 100% | Asritha Pallapotu
69 | 4. Job posting and Searching | 4.2 | Manage Job Application | Enable filtering and sorting of orders | N | 2025-04-10 | 2025-04-12 | 100% | Dhvani Dilipbhai Borda
70 | 4. Job posting and Searching | 4.2 | Manage Job Application | Build UI feedback for order transitions | Y | 2025-04-10 | 2025-04-12 | 100% | Jensikumari Ishvarbhai Jasoliya
71 | 4. Job posting and Searching | 4.2 | Manage Job Application | Conduct regression testing for order management | Y | 2025-04-10 | 2025-04-11 | 100% | Syed Adnan
72 | 4. Job posting and Searching | 4.2 | Manage Job Application | Display active/completed orders dynamically | Y | 2025-04-10 | 2025-04-11 | 100% | Asritha Pallapotu
73 | 4. Job posting and Searching | 4.2 | Manage Job Application | Implement logic to mark order statuses | Y | 2025-04-11 | 2025-04-12 | 100% | Dhvani Dilipbhai Borda
74 | 4. Job posting and Searching | 4.2 | Manage Job Application | Enable filtering and sorting of orders | Y | 2025-04-11 | 2025-04-13 | 100% | Yugantkumar Gajera
75 | 4. Job posting and Searching | 4.2 | Manage Job Application | Build UI feedback for order transitions | Y | 2025-04-11 | 2025-04-13 | 100% | Naveen Kumar Kukutla
76 | 4. Job posting and Searching | 4.2 | Manage Job Application | Conduct regression testing for order management | Y | 2025-04-11 | 2025-04-13 | 100% | Naveen Kumar Kukutla

## Sprint-3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 4.Job Posting and Searching | 4.4 | Search Job by Keywords | Create a responsive input field for keywords on the job listing page. | Y | 2025-04-17 | 2025-04-19 | 100% | Asritha Pallapotu
2 | 4.Job Posting and Searching | 4.4 | Search Job by Keywords | Develop an endpoint that accepts keywords and returns matching jobs. | Y | 2025-04-17 | 2025-04-17 | 100% | Syed Adnan
3 | 4.Job Posting and Searching | 4.4 | Search Job by Keywords | Connect frontend search bar to the backend using Axios/Fetch. | N | 2025-04-17 | 2025-04-18 | 100% | Sai Aneesh
4 | 4.Job Posting and Searching | 4.4 | Search Job by Keywords | Implement keyword search using SQL LIKE, or integrate Elasticsearch for smarter results. | N | 2025-04-17 | 2025-04-19 | 100% | Dhvani Dilipbhai Borda
5 | 4.Job Posting and Searching | 4.4 | Search Job by Keywords | Show keyword suggestions as user types. | Y | 2025-04-17 | 2025-04-18 | 100% | Naveen Kumar Kukutla
6 | 4.Job Posting and Searching | 4.4 | Search Job by Keywords | Bold or color-match keywords in results for better visibility. | N | 2025-04-18 | 2025-04-19 | 100% | Yugantkumar Gajera
7 | 4.Job Posting and Searching | 4.4 | Search Job by Keywords | Display “No jobs found” message with alternative suggestions. | N | 2025-04-18 | 2025-04-18 | 100% | Sai Aneesh
8 | 4.Job Posting and Searching | 4.4 | Search Job by Keywords | Produce test specifications for search functionality. | Y | 2025-04-18 | 2025-04-20 | 100% | Asritha Pallapotu
9 | 4.Job Posting and Searching | 4.4 | Search Job by Keywords | Trim whitespace, sanitize inputs to avoid injection. | N | 2025-04-18 | 2025-04-18 | 100% | Naveen Kumar Kukutla
10 | 4.Job Posting and Searching | 4.4 | Search Job by Keywords | Test search accuracy, performance, and user experience. | Y | 2025-04-18 | 2025-04-19 | 100% | Yugantkumar Gajera
11 | 4.Job Posting and Searching | 4.5 | Filter Jobs by Criteria | Build dropdowns, checkboxes, or sliders for filters like budget, location, and category. | Y | 2025-04-18 | 2025-04-20 | 100% | Syed Adnan
12 | 4.Job Posting and Searching | 4.5 | Filter Jobs by Criteria | Update job query logic to apply filters received as query params. | Y | 2025-04-18 | 2025-04-20 | 100% | Venkata Puneeth Nannapaneni
13 | 4.Job Posting and Searching | 4.5 | Filter Jobs by Criteria | Allow multi-select filters and logical combinations (AND/OR). | Y | 2025-04-18 | 2025-04-18 | 100% | Sai Aneesh
14 | 4.Job Posting and Searching | 4.5 | Filter Jobs by Criteria | Provide a “Clear All Filters” button to reset selections. | Y | 2025-04-18 | 2025-04-19 | 100% | Yugantkumar Gajera
15 | 4.Job Posting and Searching | 4.5 | Filter Jobs by Criteria | Connect filter changes to API and update job list in real-time. | Y | 2025-04-18 | 2025-04-20 | 100% | Jensikumari Ishvarbhai Jasoliya
16 | 4.Job Posting and Searching | 4.5 | Filter Jobs by Criteria | Produce test specifications for job Filter functionality. | N | 2025-04-18 | 2025-04-20 | 100% | Amar Gopal Kapalavai
17 | 4.Job Posting and Searching | 4.5 | Filter Jobs by Criteria | Ensure paginated results respect active filters. | Y | 2025-04-18 | 2025-04-20 | 100% | Sai Aneesh
18 | 4.Job Posting and Searching | 4.5 | Filter Jobs by Criteria | Pre-fill filters based on saved preferences or location. | Y | 2025-04-18 | 2025-04-18 | 100% | Dhvani Dilipbhai Borda
19 | 4.Job Posting and Searching | 4.5 | Filter Jobs by Criteria | Verify filters when no jobs match, invalid values, etc. | N | 2025-04-18 | 2025-04-19 | 100% | Dhvani Dilipbhai Borda
20 | 4.Job Posting and Searching | 4.6 | Save Favourite Job | Add heart/bookmark icon on job cards and details page. | N | 2025-04-19 | 2025-04-20 | 100% | Dhvani Dilipbhai Borda
21 | 4.Job Posting and Searching | 4.6 | Save Favourite Job | Toggle favorite state and reflect instantly on UI. | Y | 2025-04-19 | 2025-04-20 | 100% | Jensikumari Ishvarbhai Jasoliya
22 | 4.Job Posting and Searching | 4.6 | Save Favourite Job | Create POST/GET/DELETE routes for managing saved jobs. | N | 2025-04-19 | 2025-04-19 | 100% | Asritha Pallapotu
23 | 4.Job Posting and Searching | 4.6 | Save Favourite Job | Display user’s saved jobs in their dashboard. | N | 2025-04-19 | 2025-04-20 | 100% | Asritha Pallapotu
24 | 4.Job Posting and Searching | 4.6 | Save Favourite Job | Ensure only logged-in users can save jobs. | Y | 2025-04-19 | 2025-04-20 | 100% | Akhil Yadati
25 | 4.Job Posting and Searching | 4.6 | Save Favourite Job | Prevent the same job from being saved multiple times. | Y | 2025-04-19 | 2025-04-19 | 100% | Sai Aneesh
26 | 4.Job Posting and Searching | 4.6 | Save Favourite Job | Add visual cues when job is saved/removed from favorites. | Y | 2025-04-19 | 2025-04-20 | 100% | Asritha Pallapotu
27 | 4.Job Posting and Searching | 4.6 | Save Favourite Job | Test save/unsave functionality for different scenarios. | Y | 2025-04-20 | 2025-04-20 | 100% | Amar Gopal Kapalavai
28 | 6. Freelancer-Client linking | 6.3 | Negotiate Project Terms | Build a modal/form where terms like budget and duration can be proposed. | N | 2025-04-20 | 2025-04-21 | 100% | Akhil Yadati
29 | 6. Freelancer-Client linking | 6.3 | Negotiate Project Terms | Store negotiation offers with timestamps and user roles. | Y | 2025-04-20 | 2025-04-22 | 100% | Jensikumari Ishvarbhai Jasoliya
30 | 6. Freelancer-Client linking | 6.3 | Negotiate Project Terms | Enable a threaded view of negotiation history. | Y | 2025-04-20 | 2025-04-23 | 100% | Syed Adnan
31 | 6. Freelancer-Client linking | 6.3 | Negotiate Project Terms | Add actions to accept or reject terms and lock them. | N | 2025-04-20 | 2025-04-20 | 100% | Amar Gopal Kapalavai
32 | 6. Freelancer-Client linking | 6.3 | Negotiate Project Terms | Notify involved users of new proposals or changes. | Y | 2025-04-21 | 2025-04-22 | 100% | Sai Aneesh
33 | 6. Freelancer-Client linking | 6.3 | Negotiate Project Terms | Keep a log of all negotiation changes for reference. | Y | 2025-04-21 | 2025-04-22 | 100% | Asritha Pallapotu
34 | 6. Freelancer-Client linking | 6.3 | Negotiate Project Terms | Ensure budget and deadline values are logical and secure. | N | 2025-04-21 | 2025-04-22 | 100% | Naveen Kumar Kukutla
35 | 6. Freelancer-Client linking | 6.3 | Negotiate Project Terms | Simulate negotiation flows with different users. | N | 2025-04-21 | 2025-04-22 | 100% | Yugantkumar Gajera
36 | 6. Freelancer-Client linking | 6.4 | Real-Time Communication | Configure Firebase, Socket.IO, or alternative for real-time updates. | N | 2025-04-22 | 2025-04-23 | 100% | Jensikumari Ishvarbhai Jasoliya
37 | 6. Freelancer-Client linking | 6.4 | Real-Time Communication | Create chat layout with message bubbles and timestamps. | Y | 2025-04-22 | 2025-04-24 | 100% | Amar Gopal Kapalavai
38 | 6. Freelancer-Client linking | 6.4 | Real-Time Communication | Implement live messaging functionality between users. | Y | 2025-04-22 | 2025-04-25 | 100% | Sai Aneesh
39 | 6. Freelancer-Client linking | 6.4 | Real-Time Communication | Produce test specifications for Communication Real-Time functionality. | Y | 2025-04-23 | 2025-04-26 | 100% | Dhvani Dilipbhai Borda
40 | 6. Freelancer-Client linking | 6.4 | Real-Time Communication | Save chats in the database for history tracking. | N | 2025-04-24 | 2025-04-25 | 100% | Dhvani Dilipbhai Borda
41 | 6. Freelancer-Client linking | 6.4 | Real-Time Communication | Show when the other user is typing (real-time hint). | Y | 2025-04-25 | 2025-04-25 | 100% | Dhvani Dilipbhai Borda
42 | 6. Freelancer-Client linking | 6.4 | Real-Time Communication | Mark messages as read when seen. | N | 2025-04-25 | 2025-04-26 | 100% | Jensikumari Ishvarbhai Jasoliya
43 | 6. Freelancer-Client linking | 6.4 | Real-Time Communication | Add optional support for file/image sharing. | N | 2025-04-25 | 2025-04-26 | 100% | Asritha Pallapotu
44 | 6. Freelancer-Client linking | 6.4 | Real-Time Communication | Encrypt chat messages or ensure SSL connection. | Y | 2025-04-26 | 2025-04-26 | 100% | Asritha Pallapotu
45 | 6. Freelancer-Client linking | 6.5 | Suggests Relevant Jobs | Identify which profile elements (skills, location, etc.) affect matching. | N | 2025-04-26 | 2025-04-27 | 100% | Asritha Pallapotu
46 | 6. Freelancer-Client linking | 6.5 | Suggests Relevant Jobs | Create a function or model that ranks job relevance. | N | 2025-04-27 | 2025-04-27 | 100% | Syed Adnan
47 | 6. Freelancer-Client linking | 6.5 | Suggests Relevant Jobs | Develop endpoint to return recommended jobs for logged-in users. | Y | 2025-04-27 | 2025-04-27 | 100% | Sai Aneesh
48 | 6. Freelancer-Client linking | 6.5 | Suggests Relevant Jobs | Create a “Suggested Jobs” section on the freelancer dashboard. | Y | 2025-04-28 | 2025-04-30 | 100% | Dhvani Dilipbhai Borda
49 | 6. Freelancer-Client linking | 6.5 | Suggests Relevant Jobs | Produce test specifications for job Relevant functionality. | N | 2025-04-29 | 2025-04-30 | 100% | Naveen Kumar Kukutla
50 | 6. Freelancer-Client linking | 6.5 | Suggests Relevant Jobs | Add thumbs up/down to improve recommendation accuracy. | N | 2025-04-30 | 2025-04-30 | 100% | Dhvani Dilipbhai Borda
51 | 6. Freelancer-Client linking | 6.5 | Suggests Relevant Jobs | Adjust future recommendations based on feedback and behavior. | N | 2025-04-30 | 2025-05-01 | 100% | Jensikumari Ishvarbhai Jasoliya
52 | 6. Freelancer-Client linking | 6.5 | Suggests Relevant Jobs | Refresh suggestions automatically when the profile is updated. | N | 2025-05-01 | 2025-05-02 | 100% | Asritha Pallapotu
53 | 6. Freelancer-Client linking | 6.5 | Suggests Relevant Jobs | Test with different user profiles to validate accuracy and performance. | N | 2025-05-01 | 2025-05-02 | 100% | Asritha Pallapotu