## Road Map
FREELANCE FORGE
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 3/26/2025 | SPRINT2 - 4/16/2025 | SPRINT3 - 5/7/2025
1. Freelancer Registration | 1.1 Collect Freelancer Information | 2 | X
| 1.2 Verify Freelancer Identity | 2 | X
| 1.3 Create Freelancer Profile | 4 | X
1.4 Onboarding Process
2. Client Registration | 2.1 Create client profile | 4 | X
| 2.2 Verify Client identity | 2 | X
| 2.3 Collect Client information | 2 | X
3. Account Management | 3.1 Account Deactivation/Reactivation
| 3.2 Account Settings | 4 |  | X
| 3.3 Profile update and management | 3 |  | X
| 3.4 login/logout functionality | 4 | X
4. Job posting and searching | 4.1 Create job posting | 4 |  | X
| 4.2 Manage job application | 3 |  | X
| 4.3 Select Freelancer for the job | 2 |  | X
| 4.4 Search job by keywords | 4 |  |  | X
| 4.5 Filter jobs by criteria | 4 |  |  | X
| 4.6 Save Favourite job | 2 |  |  | X
5. Subscription Management | 5.1 Define Subscription tiers
5.2 Set pricing for each tiers
5.3 Process Subscription payments
5.4 Manage User subscriptions
6. Freelancer-client linking | 6.1 Suggests relevant freelancer | 2 |  | X
| 6.2 Submit proposals for jobs | 2 |  | X
| 6.3 Negotiate project terms | 2 |  |  | X
| 6.4 Real time communication | 4 |  |  | X
| 6.5 Suggests Relevant jobs | 4 |  |  | X
|  | VELOCITY: | 20 | 20 | 20

## Jira Road Map
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board